## Sheet1
Work Breakdown Structure
Task | Completion Date
Rough storyline | 2016-10-03
Storyline complete | 2016-10-09
Level ending code | 2016-10-09
Checkpoint code | 2016-10-09 | x
Weekly new enemy | 2016-10-09
Weekly new enemy | 2016-10-16
Biweekly new powerup | 2016-10-16
Biweekly new boss | 2016-10-16
Weekly new enemy | 2016-10-23 |  |  | 32x32 | original dude sprite size
Level HUD | 2016-10-23 |  |  | 400x240 | view size
Title screen | 2016-10-23
Main menu | 2016-10-23
Weekly new enemy | 2016-10-30
Biweekly new powerup | 2016-10-30
Biweekly new boss | 2016-10-30 |  | Need Dates | Turtle Powerups
How to get new shell | 2016-10-30
Weekly new enemy | 2016-11-06 |  |  | Volcanic Turtle |  | shoots fireballs out of top when sliding
Point system | 2016-11-06 |  |  | Turtle Knight |  | turtle shell is a shield that can be held in front
Weekly new enemy | 2016-11-13 |  |  | Turtle Ninja |  | Can jump off walls (sort of like mario)
Biweekly new powerup | 2016-11-13 |  |  | Electric Turtle |  | can blink/teleport forward when sliding
Biweekly new boss | 2016-11-13 |  |  | Magnet Turtle? |  | press a button to stick to certain surfaces
Weekly new enemy | 2016-11-20 |  |  | Mud turtle |  | cannot slow down as fast (grease turtle)
Level selection screen | 2016-11-20 |  |  | Snowball turtle? |  | can throw snowballs or turn into a rolling snowball
Weekly new enemy | 2016-11-27 |  |  | companion powerup (squirrel or something)
Biweekly new powerup | 2016-11-27 |  |  | sticky shell
Biweekly new boss | 2016-11-27 |  |  | jump out of shell mid air ( might just be a regular thing)
Weekly new enemy | 2016-12-04 |  |  | shell with rope (explorer turtle?)
Save system | 2016-12-04 |  |  | spiked shell
Weekly new enemy | 2016-12-11
Biweekly new powerup | 2016-12-11 |  |  |  | Areas/Themes
Biweekly new boss | 2016-12-11 |  |  |  | Jungle
Weekly new enemy | 2016-12-18 |  |  |  | Desert
Weekly new enemy | 2016-12-25 |  |  |  | Frozen
Biweekly new powerup | 2016-12-25 |  |  |  | Burning/Volcanic
Biweekly new boss | 2016-12-25 |  |  |  | Tech/Electricity
Weekly new enemy | 2017-01-01 |  |  |  | Beach
Weekly new enemy | 2017-01-08 |  |  |  | Autumn
Biweekly new powerup | 2017-01-08 |  |  |  | Spring/Wet/Rainy
Biweekly new boss | 2017-01-08 |  |  |  | Night/Stealth
Weekly new enemy | 2017-01-15 |  |  |  | Haunted/Spooky theme
Weekly new enemy | 2017-01-22
Biweekly new powerup | 2017-01-22 |  |  |  | a rainy hide in shell level
Biweekly new boss | 2017-01-22
Weekly new enemy | 2017-01-29
Level Due | 2017-02-01